Project Charter

| Project Name | Cilekler: HTML-Based Digital Storytelling Game for Engagement in Museum |
| --- | --- |
| Project ID | CILEKLER_2026 |
| Grantor / Customer | Main stakeholder (customer): the commissioning museum institution. Other key stakeholders: prospective and on-site museum visitors (families, teenagers, general public), exhibition curators, museum communication and digital staff, academic supervisors. |

| Document version | Date | Contributors | State |
| --- | --- | --- | --- |
| 1.0 | 16.06.2026 | Ceyda Uyar | Draft (for review) |

1. Project Description

This project plans and manages the development of a browser-based interactive storytelling game commissioned by a museum to increase visitor interest and attract new audiences to an upcoming exhibition. The game follows a time detective narrative theme explicitly requested by the institution to align with the exhibition's subject matter. Players engage with branching story choices that reveal historically grounded clues, culminating in an invitation to visit the museum and experience the full exhibition in person.

The product is authored using Twine, an open-source tool for non-linear interactive fiction, and delivered as a standalone HTML/CSS website accessible through any standard browser  no installation required. Image and sound assets are generated specifically for the project's visual and narrative identity, creating a cohesive aesthetic experience. The project is a four-person academic team effort conducted within the Master's programme in Digital Humanities and Digital Knowledge (DHDK) at the University of Bologna.

2. Project Scope

In scope:

- A complete, playable Twine-based branching narrative structured as a time detective story, with multiple decision points and at least two distinct endings.

- Conversion of the Twine story map into a fully functional, styled HTML/CSS website deployable via GitHub Pages or equivalent static hosting.

- A set of original AI-generated images and sound assets integrated into the gameplay experience to support atmosphere and narrative immersion.

- Thematic alignment with the museum's upcoming exhibition: story events, characters, and clues must be inspired by or consistent with the exhibition's historical or cultural subject matter.

- Game accessibility through a QR code link, enabling deployment both on the museum's website and as a physical prompt at the exhibition entrance.

- Project management documentation covering all phases from initiation through delivery.

Out of scope:

- Back-end infrastructure, databases, or user account systems.

- Native mobile app development.

- Full multilingual localisation (an Italian-language version may be considered as a stretch goal).

- Real-time analytics or visitor data collection.

3. Deliverable List

- Project Charter (this document)

- Gantt diagram

- Software Requirements Specification (SRS)

- System architecture diagram and application diagram

- Sample use case

- Testing methodology description and a test case

- Slideshow presenting the project to the team

- User manual (sample UI flow documentation)

- Playable prototype (hosted on GitHub: https://github.com/GrandTuvalet/Cilekler)

4. Constraints

- Team size and timeline: the project is developed by four students within an academic semester; scope is bounded by available person-hours.

- Toolchain constraints: the project uses Twine as the authoring environment; the final output must remain a static HTML/CSS product with no server-side dependencies.

- Content approval dependency: narrative content referencing specific historical artefacts or exhibition themes requires institutional sign-off, which may introduce delays.

- Asset licensing: all images and audio assets must be original (AI-generated) or free to use, to avoid copyright issues in a public-facing museum context.

- No user data collection: the game must not collect, store, or transmit any personally identifiable information (PII), in compliance with institutional and academic privacy obligations.

5. Risk Analysis

| Key Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Narrative scope creep story branches grow too large to complete | High | High | Define a fixed maximum number of passages and endings at the outset; use Twine's story map to enforce limits. |
| Content approval delays from the museum | Medium | High | Use placeholder or fictional references during development; submit for review early. |
| Visual/audio asset quality inconsistency | Medium | Medium | Establish a visual style guide and asset generation parameters before production begins; review assets as a team. |
| HTML conversion breaks Twine logic or styling | Medium | High | Test the converted website at each integration step; maintain a clean backup of the original Twine source file. |
| Team coordination issues in a four-person remote workflow | Medium | Medium | Use GitHub for version control; define clear handoff points between story authoring, Twine mapping, and HTML development phases. |
| Game unplayable on certain browsers or devices | Low | High | Test on Chrome, Firefox, and Safari at both desktop and mobile resolutions before delivery. |

6. Work Breakdown Structure

1. Initiation

- 1.1 Stakeholder analysis and institutional requirements gathering

- 1.2 Project charter and definition of success criteria

2. Requirements

- 2.1 Elicitation of functional and non-functional requirements

- 2.2 SRS drafting and prioritisation

- 2.3 Requirements review

3. Narrative and Conceptual Design

- 3.1 Story concept and time detective scenario definition

- 3.2 Conceptual art direction: mood, colour palette, visual identity

- 3.3 Story script and branching structure (passages, choices, endings)

4. Asset Production

- 4.1 AI-generated image assets (characters, scenes, UI elements)

- 4.2 Sound assets (ambient audio, interaction feedback)

- 4.3 Asset integration review and optimisation

5. Twine Implementation

- 5.1 Story map construction in Twine (passages, links, variables)

- 5.2 Internal playthrough testing and narrative coherence review

- 5.3 Export of Twine output for web adaptation

6. HTML/CSS Development

- 6.1 Adaptation of Twine export into a styled website

- 6.2 Asset embedding (images, audio, fonts)

- 6.3 Responsive design and cross-browser testing

7. Verification and Validation

- 7.1 Functional testing of all story branches and endings

- 7.2 Usability review against museum audience requirements

- 7.3 Acceptance check against SRS

8. Delivery

- 8.1 Deployment to GitHub Pages

- 8.2 Final documentation package

- 8.3 Presentation slideshow

7. Resources

Human Resources

| Role | Responsibilities | Team Member |
| --- | --- | --- |
| Project Manager / Conceptual Art Director | Project coordination, conceptual art direction, AI image and sound asset generation, project management documentation | Ceyda Uyar |
| Story Writer / Presenter | Narrative script, branching story structure, dialogue writing, presentation slideshow | Daniele Camagna |
| Twine Developer | Story map construction in Twine, passage logic, variable management, internal testing | Dinara Kabiyeva |
| Web Developer | Conversion of Twine export to HTML/CSS website, styling, asset integration, deployment | Atakan Kayi |

Technical Resources

- Twine (open-source, free): story authoring and non-linear map construction

- GitHub / GitHub Pages: version control and static web hosting

- AI image generation tools: original visual asset creation

- Audio generation / free audio tools: ambient sound and interaction audio

- Standard web browsers: development and testing environment

8. Financial Budget

Cost figures are based on current freelance and agency market rates for small-scale interactive digital storytelling projects in the cultural heritage sector (comparable range: €8,000-15,000 for browser-based museum digital engagement tools). Since this is an academic project, all labour is contributed by the team at no cost; the figures below reflect what equivalent work would cost in a professional context.

| Budget Category | Items | Market-Rate Total (€) |
| --- | --- | --- |
| Human Resources (Labour) | 7 roles, 48 person-days total | 12,800 |
| Tools and Infrastructure | 8 items | 200 |
| Content and Materials | 5 items | 100 |
| Contingency Reserve (10%) | Risk buffer | 1,300 |
| GRAND TOTAL |  | € 14,400 |