## Gantt Chart
CILEKLER an HTML-Based Digital Storytelling Game for Museum Engagement
PROJECT MANAGER: Ceyda Uyar
WBS | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1. INITIATION
1.1 | Stakeholder analysis & objectives | Ceyda (PM) | 01/04/2026 | 04/04/2026 | 3
1.2 | Project charter & success criteria | Ceyda (PM) | 03/04/2026 | 07/04/2026 | 4
2. REQUIREMENTS
2.1 | Requirements elicitation | Ceyda (PM) | 07/04/2026 | 11/04/2026 | 4
2.2 | SRS drafting & prioritisation | Ceyda (PM) | 10/04/2026 | 16/04/2026 | 6
2.3 | Requirements review | Whole Team | 15/04/2026 | 17/04/2026 | 2
3. NARRATIVE & DESIGN
3.1 | Story concept & time detective scenario | Writer | 07/04/2026 | 11/04/2026 | 4
3.2 | Art direction & visual identity | Ceyda (Art) | 10/04/2026 | 14/04/2026 | 4
3.3 | Full story script & branch structure | Writer | 11/04/2026 | 19/04/2026 | 8
3.4 | Twine passage map design | Twine Dev | 16/04/2026 | 19/04/2026 | 3
4. ASSET PRODUCTION
4.1 | AI image asset generation | Ceyda (Art) | 14/04/2026 | 24/04/2026 | 10
4.2 | Sound & ambient audio generation | Ceyda (Art) | 18/04/2026 | 24/04/2026 | 6
4.3 | Asset review & optimisation | Ceyda (Art) | 24/04/2026 | 26/04/2026 | 2
5. TWINE DEVELOPMENT
5.1 | Twine story map construction | Twine Dev | 19/04/2026 | 28/04/2026 | 9
5.2 | Internal playthrough & branch testing | Twine Dev | 28/04/2026 | 30/04/2026 | 2
6. HTML/CSS DEVELOPMENT
6.1 | HTML/CSS conversion of Twine export | Web Dev | 30/04/2026 | 09/05/2026 | 9
6.2 | Asset embedding & visual styling | Web Dev | 07/05/2026 | 13/05/2026 | 6
6.3 | Responsive & cross-browser testing | Web Dev | 13/05/2026 | 17/05/2026 | 4
7. VERIFICATION & VALIDATION
7.1 | Functional branch & logic testing | Whole Team | 13/05/2026 | 17/05/2026 | 4
7.2 | Usability & audience review | Whole Team | 17/05/2026 | 19/05/2026 | 2
7.3 | Acceptance check vs SRS | Ceyda (PM) | 19/05/2026 | 21/05/2026 | 2
8. DELIVERY
8.1 | GitHub Pages deployment | Web Dev | 21/05/2026 | 23/05/2026 | 2
8.2 | Final documentation package | Ceyda (PM) | 19/05/2026 | 23/05/2026 | 4
8.3 | Presentation slideshow | Writer | 19/05/2026 | 23/05/2026 | 4